## Sheet1
Sr.No | Module | Sub Module | Developer | Completed Date
1 | Gmail integration | gmail api authitincation | Ramesh | 2022-09-15
|  | local pc gmail source code api testing | Ramesh
|  | read gmail inbox and get list of emails | Ramesh
|  | create new web pages to view and fillter inbox | Ramesh
|  | search for paticuler health reports /email only | Ramesh
|  | store data into Howzu System | Ramesh
|  | production testing with gmail API & approval from gmail | Ramesh
|  | OCR Code implementation get Test Reprot from Gmail inbox | Ramesh | 2022-09-30
|  | code published | Ramesh
|  | Api integration with HowzU App | Vijay Rane
|  | integration testing Howzu APP | Vijay Rane
Go to Live
2 | Images Upload | RnD on Images Upload code on .net core 3.1 apis | Harshada | 2022-09-06
|  | Code implementation and API Creation | Harshada
|  | api published and testing | Harshada
|  | api integration with HowzU App | Vijay Rane
3 | Whatsapp integrration | whastapp multimedia msgs | Harshada | 2022-09-15
|  | whatsapp 2 way communication | Harshada
|  | webhook creation and implementation | Harshada | 2022-09-30
|  | flow creation and connect flow with multiple msges | Harshada
|  | whats app templet creation and integration with HowzU Connect | Harshada
4 | OCR | Uploaded test report data match with master data | sagar | 2022-09-20
|  | Store values into database | sagar
|  | view and very values by user | sagar
|  | create api for ocr upload | sagar
|  | create new flows & screens in Howzu app | Vijay Rane
|  | api integration in howzu app | Vijay Rane
5 | ABHA Integration | ABHA api code RnD | Harshada | 2022-09-30
| - USER account Creation | Api sandbox testing | Harshada
|  | api implementation with howzu website / api | Harshada
|  | api integration testing | Harshada
|  | api integration approval from ABHA | Harshada
|  | Production Movment with ABHA Team | Harshada
6 | Testing | Pathlab load / unit testing | Urmila | 2022-09-30
|  | Enterprise Load / unit testing | Urmila
|  | API Load / unit Testing | Urmila
7 | Application Support | Enterprise Dashboard | Harshada | On Going
|  | HowzU API | Harshada
|  | Pathlab | Ramesh
|  | MIS Dashboard | Ramesh
|  | HowzU Mobile App | Vijay Rane
8 | HowzU App | User Registration form changes |  | 2022-09-30